# Design Status Memorandum:

- Objectives: The main objective of this project is enhancing the previously built rover, which is battery powered, by integrating solar power, autonomous power switching between solar and battery power, and an independent cleaning system for the solar panel.

Major Deliverables Promised: Upon completion of our project, we will be delivering a functional solar power system which will be added onto the existing planetary exploration rover LOUIS. This solar power system will have autonomous power switching between battery and solar power, depending on available sunlight and user preference. We will also have an autonomous cleaning system incorporated into our design to clean the solar panel of dust or debris which will be activated when it is detected to be dirty. Our team will ensure that the additions we make will only be improvements to the rover, without losing any of the general functionality existing prior to our additions. Other deliverables include comprehensive reports and presentations, as well as complete engineering analyses detailing the technical aspects of the project.

General Timeline: Since the start of our project, our team has surpassed the planning stages of the project, and we are now in the analysis stage of our project. Here, we plan to verify the feasibility of our project. To do so, our group has devised certain analyses that aim to test the feasibility of our functions. These analyses involve simulations and calculations that will produce specific results and scenarios that we can analyze to drive our project to the next stage. Moving forward to the Spring 2025 Semester, our team is aiming to reach the manufacturing and testing stages of our project. During the manufacturing stage, our team is expecting to receive all ordered items to begin the assemblies of our functions, which will then be implemented onto our existing rover. Once our manufacturing is complete, we hope to test these functions and full system during the testing stage of the project. For testing, our group aims to put our functions and systems through a multitude of real-world scenarios that we can observe and collect data from based on the performances that our systems yield. Using this data and testing, we will be able to fine-tune and finalize our rover for peak performance.

Summary Statement:

We have made changes to our design to incorporate feedback from the final presentation in the fall. The added complexity of the project has brought with it a few small setbacks, which is to be expected. We have also addressed a few issues that were not apparent to us until we were able to physically look at the components we ordered. Also, as we continue to assemble the project, we have continued to find that we needed to order additional components to complete the manufacturing process. These factors combined have put us slightly behind schedule. However, the team anticipates a large portion of the work to be completed rather quickly once all the necessary components have been delivered.

Accomplished Work:

So far, the team has made and configured the website, which can be accessed through the following link: https://megburkes1.github.io/LOUIS/. This includes the following tabs that will be updated as new information becomes available: home, how to work LOUIS, maintenance instructions, parts list, and reference information. The charge controller has been programmed and is being awaited testing before fully implementing it into our system. The pyranometer and camera platform model has been designed and is awaiting 3D printing. The gantry plate to fit the gearmotor has been designed and is awaiting the CNC milling machine. The rover’s breaker has also been fixed, since it broke last semester. Some of the wiring has been completed for the stepper motors. Most of the Arduino has been coded, except for the comparison of outputs between the pyranometer and the solar panel. The linear actuators have been constructed, and the mounting bars have been cut. A custom-made flange has been designed, but it is awaiting machining. The solar panel power output testing has begun, but we will need multiple days and time of day to have a full picture of its functionality and behavior. The results, thus far, can be seen below, where the performance ratio is calculated using the following formula: Performance Ratio=Measured PowerRated Power.

|  | Voltage | Current | Power | Day | Time | Performance Ratio |
| --- | --- | --- | --- | --- | --- | --- |
| Trial 1 | 60.31 V | 6.99A | 421.57 W | 2/25/25 | 11:33 AM | 93.68% |
| Trial 2 | 60.56 V | 7.06A | 427.55 W | 2/25/25 | 11:39 AM | 95.01% |

Remaining Work:

- The remaining work includes: the gantry plate manufacturing. The welding of linear rails to the solar panel. Final assembly of the cleaning system. The construction of custom flanges for the brush. The combination of several components such as the previously mentioned linear rails to the linear actuating rails. Non-ideal condition test and an artificial light test for the solar panels power output has yet to be done.

Time and Resources Planned:

The manufacturing of the gantry plate and welding is planned to be completed by Keldon and Willliam in the machine shop during the next several work sessions. The assembly of the cleaning system will continue to be worked on by the entire team, as all team members are working on various aspects of the cleaning system. A work order will be placed within the next week to get our custom flanges machined for attaching the brush to the rotational motor. The team would like to reserve the last few weeks of the semester for testing the entire solar power system in varying conditions.

| OBJECTIVES | DELIVERABLES* | WORK ITEMS | TIMELINE PROGRESS |
| --- | --- | --- | --- |
| Addition of solar power to the rover | Functional solar power system capable of switching between solar and battery power as needed | 1. Choose a specific solar panel and charge controller. 2. Determine method of power switching. | 100% |
| Self-cleaning of the solar panel | Cleaning system to automatically remove dust or debris that could be detrimental to power generation | 1. Purchase custom parts, such as the brush and long rails for the linear actuators. 2. Determine how to mount components to the rover. 3. Size motors & run Simulink simulations. | 100% |
| - Manufacture cleaning system | - Manufacture the previously designed cleaning system. | - Assemble gantry plates to mounting plates - Attach brush via custom flange to rotational motors - Attach the cleaning system to solar panel | - 50% |
| - Solar Power Implementation | - The Solar panel will be mounted to the rover and will provide power | - Mount solar panel and cleaning system to rover - Conduct power output test and compare it to power draw | - 20% |

Summary Table for This Semester:

*Deliverables shown are only those specific to the respective objectives, not including reports/analyses for the project as a whole.

Major Changes/Challenges:

One of the main changes/challenges to our project came after the final presentation from the previous semester. Our team previously planned on activating our cleaning system using a timer-based Arduino activation, however, the judging panel requested that we add more complexity to the activation portion of our cleaning system. To adjust to this request, our group spent some time planning and redesigning to ultimately come up with a system designed to compare the results of a pyranometer and the power output of the solar panel. We plan on using look up tables to compare the values of the pyranometer to the power output of the solar panel. If any differences are seen, the Arduino code informs the system to begin a cleaning cycle for the solar panel. Aside from this change, our group hasn’t really faced any major challenges during this Senior Design process.